## 2023FINAL
| GOALS | OBJECTIVES | PROGRAMME(PBB) | SUB-PROGRAMME (PBB) | BROAD ACTIVITIES/PROJECTS | Location | QUARTERLY TIME SCHEDULE |  |  |  | COST | [5 empty] | Programme Status |  | Implementing Dept./Unit
[7 empty] | 1ST | 2ND | 3RD | 4TH | IGF | GoG | DACF | DACF-REF | DP | Others | New | On-Going | Lead | Collaborating
1 | Build a Prosperous Country | Ensure improved fiscal performance and sustainability | Economic Development | Trade, Industry and Tourism and Industrial Development | Stakeholder forum on LED activities | District Assembly Conference hall |  | x | x |  | 0 |  | 25000 | 0 | 0 | 0 |  |  | BAC | DA
2 |  |  |  |  | MSE Sub-Committee Meeting | District Assembly Conference hall | x |  | x | x | 0 |  | 4500 | 0 | 0 | 0 |  |  | BAC | DA
3 |  |  |  |  | Business Counselling | Breman Asikuma | x | x | x | x | 0 | 2000 |  | 0 | 0 | 0 |  |  | BAC | DA/GEA
4 |  | Pursue flagship industrial development initiatives |  |  | NVTI Examination | District wide | x |  | x |  |  |  | 20000 | 0 | 0 | 0 |  |  | BAC | DA
5 |  |  |  |  | Training in Formationand Strengthening of Association | BAC |  | x | x |  | 0 | 5000 |  | 0 | 0 | 0 |  |  | BAC | DA
6 |  |  |  |  | Entrepreneurship and Financial mangement training | BAC | x |  | x |  | 0 |  | 7000 | 0 | 0 | 0 |  |  | BAC | DA/GEA
7 |  | Enhance application of ICT in national development |  |  | Provision of Technical | BAC | x |  |  | x | 0 |  | 8000 | 0 | 0 | 0 |  |  | BAC | DA/GEA
8 |  |  |  |  | Provision of start-up kits for A2E graduates | BAC |  | x |  |  |  |  | 50000 |  |  | 0 |  |  | BAC | GEA/Mastercard
9 |  |  |  |  | GEA Client Registration | BAC | x | x | x | x |  |  | 1000 |  |  | 0 |  |  | BAC | GEA
10 |  |  |  |  | GJS training for Beneficiaries | BAC |  | x |  |  |  |  | 3000 |  |  | 0 |  |  | BAC | GEA
11 |  |  |  |  | Facilitate Access Credit | BAC | x | x | [6 empty] | 500000 | 0 |  |  | BAC | REP/GEA
12 |  | Ensure efficient transmission and distribution system |  |  | Formalization of Business | BAC | x | x | x | x | 0 |  | 10000 | 0 | 0 | 0 |  |  | BAC | GEA
13 |  |  |  |  | Undertake 12No. monthly market readings on selected items | Asikuma, Odoben and Brakwa markets. | x | x | x | x | 1000 | 2602.73 | 0 | 0 | 0 | 0 |  |  | STATS. | DA
14 |  |  |  |  | Undertake 4No. enumeration of taxable properties and services | All Towns/Area Councils | x | x |  |  | 3342 | 4523.9 | 0 | 0 | 0 | 0 |  |  | STATS. | DA
15 |  |  |  |  | Evaluation of programmes executed and reporting | Asikuma-Odoben-Brakwa |  |  |  | x | 2000 | [7 empty] | CNC | DA
16 |  |  |  |  | Cultral Unity programme for basics schools. 3 days workshop on wearing of traditional clothes | Asikuma-Odoben-Brakwa |  |  | x |  | 2500 | [7 empty] | CNC | DA
17 |  |  |  |  | Identification and codification on tourism potential continues | Asikuma-Odoben-Brakwa |  | x |  |  | 3200 | [7 empty] | CNC | DA
18 |  | Diversify and expand the tourism industry for economic development |  |  | Develop 1No. database of trained apprentices and artisans within the District. | All Towns/Area Councils | x | x | x |  | 1987.86 | 7182.63 | 0 | 0 | 0 | 0 |  |  | STATS. | DA
19 |  |  |  |  | Production of 10,000No. oil palm seedlings for distribution to farmers by Dec. [Planting for Export & Rural Dev't (PERD)] | All Towns/Area Councils | √ | √ | √ | √ | 35000 |  |  | 0 |  | 0 |  |  | MoFA | DA
20 |  |  |  |  | Identification of tourist sites and potentials | Asikuma-Odoben-Brakwa | x |  |  |  | 3000 | [7 empty] | CNC | DA
21 |  |  |  |  | Conduct 2,100 farm and home visit by 14 AEAs annually by | Asikuma-Odoben-Brakwa | [12 empty] | MOFA | DA
22 |  |  |  |  | Monitoring and supervise farmers on Planting for Food and Jobs and programme annually | MoFA | x | x | x | x | 35000 |  |  | 0 |  | 0 |  |  | MoFA | DA
23 |  | Improve postharvest management |  | Total | [6 empty] | 87029.86 | 21309.26 | 128500 |  | 500000
24 |  |  |  |  | Make 720 monitoring visit by 6 District Agricultural officers annually | All Towns/Area Councils | x | x | x | x | 0 |  | 0 | 0 | 16800 | 0 |  |  | MoFA | DA
25 |  |  |  |  | Measure 25 field and established yield plots annually(MRCLS) | All Towns/Area Councils | √ | √ | √ | √ | 0 |  | 0 | 0 | 7200 | 0 |  |  | MoFA | DA
26 |  | Promote livestock and poultry development for food security and income generation |  |  | Train 60 women farmers on Non-traditional farming by Dec. 2023 | All Towns/Area Councils | √ | √ | √ | √ |  |  |  | 0 | 1200 | 0 |  |  | MoFA | DA
27 |  |  |  |  | Train 50 farmers on vegetables production by Dec 2023 | All Towns/Area Councils | √ | √ | √ | √ |  |  |  | 0 | 1000 | 0 |  |  | MoFA | DA
28 |  |  |  |  | Food Base Nutrition training for selected farmers | DoA | √ | √ | √ | √ | 1542 |  |  | 0 | 5000 | 0 |  |  | MoFA | DA
29 |  |  |  |  | Organise 1No. fishers and farmers day celebration | All Towns/Area Councils |  | x |  |  | 600 | 0 | 0 | 0 | 0 | 0 |  |  | MoFA | DA
30 |  |  |  |  | Develop 1No. database for all registered farmers in the district. | All Towns/Area Councils | x | x | x | x | 766.93 | 3609.67 | 0 | 0 | 0 | 0 |  |  | STATS. | DA
31 |  |  |  | Total | [6 empty] | 2908.93 | 3609.67 | 0 | 0 | 31200 | 0
32 | Create Equal Opportunity For All | Enhance inclusive and equitable access to, and participation in quality education at all levels | Social Services Delivery | Education and Youth Development | Orgainize 1No. Orientation for the Newly recruited teachers | GES |  |  | x |  | 2630 |  | 0 | 0 |  |  |  |  | GES | DA
33 |  |  |  |  | Organize 1No. Induction training for Newly Qualified Teachers (NQT) | GES |  |  | x |  | 1000 |  | 0 | 0 |  |  |  |  | GES | DA
34 |  |  |  |  | Organize 2No. Common Core Programme (CCP) Curriculum | GES | x | x |  |  | 2000 |  | 0 | 0 |  |  |  |  | GES | DA
35 |  |  |  |  | Undertake 4No. Monitoring of Schools | All Public Schools | x | x | x | x | 1000 | [7 empty] | GES | DA
36 |  |  |  |  | Organize 1No. Orientation for JHS candidates | All Public Schools |  |  | x |  | 1000 | [7 empty] | GES | DA
37 |  |  |  |  | Organize 1No. My First Day at School | All Public Schools |  |  | x |  | 2000 | [7 empty] | GES | DA
38 |  |  |  |  | Support BECE Mock Exams | All Public Schools | X | X | X | X | 5000 | [7 empty] | GES | DA
39 |  |  |  |  | Renovation of 3No. 6unit classroom block with ancillary facilities | Asuoko, Yenkukwaa, Breman (Col. Baidoo School) | X | X | X | X |  |  | 394000 | [5 empty] | DA | GES
40 |  |  |  |  | Support GSFP and DEOC | GES | X | X | X | X | 4000 | [7 empty] | GES | DA
41 |  |  |  | Total | [6 empty] | 18630 |  | 394000 | 0
42 |  |  |  | Health Delivery | Support for HIV/AIDS Activities | District wide | x | x | x | x |  | 2000 | 0 | [5 empty] | HEALTH DIRECTORATE | DA
43 |  |  |  |  | Supply health delivery equipment to health facilities (CHPS) | District wide | x |  |  |  |  | 2000 | 0 | [5 empty] | HEALTH DIRECTORATE | DA
44 |  |  |  |  | Support for fighting COVID-19 & other infectious diseases | District wide | x | x | x | x |  | 2000 | 0 | [5 empty] | HEALTH DIRECTORATE | DA
45 |  |  |  |  | Organize 8No. workshops on Malaria control, Sexually transmitted diseases and HIV/AIDS | Assembly Conference Hall | x | x | x | x |  | 2000 | 0 | [5 empty] | HEALTH DIRECTORATE | DA
46 |  | Ensure reduction of new HIV, AIDS/STIs and other infections, especially among vulnerable groups |  |  | Organize 8No. a day’s HIV/AIDS awareness workshop | Assembly Conference Hall | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
47 |  |  |  |  | Organise 8No. Training for health staff on Tuberculosis TB/HIV management and control | Assembly Conference Hall | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
48 |  |  |  |  | Intensify 8No. Education HIV/ AIDS Counseling and testing | All Town/Area Councils | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
49 |  |  |  |  | 4No. Public Education on Endemic Disease i.e HIV /AIDS, TB, Malaria etc. | All Town/Area Councils | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
50 |  |  |  |  | Organise 2No. monitor to integrate the HIV Alert Model in lesson delivery in 52 public schools | Selected public schools | x |  |  |  |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
51 |  |  |  |  | Organize 4No. quaterly district health committee meetings | Assembly Conference Hall | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
52 |  | Improve population management |  |  | Organize 12No. monthly PHEMC | Assembly Conference Hall | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
53
54 |  |  |  | Total | [7 empty] | 22000 | 0
55 |  | Reduce disability morbidity, and mortality |  | Health Delivery | Reduce Under-five mortality rate | All Town/Area Councils | x | x | x | x |  | 1800 | [6 empty] | HEALTH DIRECTORATE | DA
56 |  |  |  |  | Reduce Maternal mortality ratio | All Town/Area Councils | x | x | x | x |  | 1800 | [6 empty] | HEALTH DIRECTORATE | DA
57 |  |  |  |  | Reduce Malaria case fatality in children under five years | All Town/Area Councils | x | x | x | x |  | 2000 | [6 empty] | HEALTH DIRECTORATE | DA
58 |  |  |  | Total | [7 empty] | 5600
59 |  | Improve access to safe and reliable water supply services for all |  | Environmental Health and sanitation Services | Update 2022-2023 District Environmental Sanitation Strategy and Action Plan (DESSAP) | DPCU Secretariat | x | x | x | x | 1390 |  | 30000 | [5 empty] | EHU &SWCD | DA
60 |  |  |  |  | Facilitate the acquisition of 1No. land for final Waste Disposal & Other Land Banks | Breman Asikuma |  | x |  |  | 1500 |  | 50000 | [5 empty] | EHU | DA
61 |  |  |  |  | Facilitate the Procument of Sanitary Tools | EHU | x | x | x | x | 1000 |  | 45000 | [5 empty] | EHU | DA
62 |  |  |  |  | Provide Sanitation Improvement Package (Zoomlion) | EHU | x | x | x | x | 1800 |  | 30000 | [5 empty] | EHU | DA
63 |  |  |  |  | Undertake 12No. Fumigation exercise | All Town/Area Councils | X | X | X | X | 2000 |  | 50000 | [5 empty] | EHU | DA
64 |  | Enhance access to improved and reliable environmental sanitation services |  |  | Evacuation of refuse dumps | Districtwide | x | x | x | x | 1021.2 |  | 20000 | [5 empty] | EHU | DA
65 |  |  |  |  | Undertake 12No. DICCS monitoring | All Town/Area Councils | X | X | X | X | 1500 |  | 48000 | [5 empty] | EHU | DA
66 |  |  |  |  | Undertake 12 No. Monthly meeting for field facilitators | Assembly Conference Hall | X | X | X | X | 2185 |  | 67000 | [5 empty] | EHU | DA
67 |  |  |  |  | Health Education and promotion | All Towns/Area Councils | x | x | x | x | 1100 |  | 41000 | [5 empty] | EHU | DA
68 |  |  |  |  | Undertake 12 No. DICCS verification | Assembly Conference Hall | X | X | X | X | 1500 |  | 49000 | [5 empty] | EHU | DA
69 |  |  |  |  | Undertake 12 No. DICCS meeting | Assembly Conference Hall | X | X | X | X | 876 |  | 23890 | [5 empty] | EHU | DA
70 |  |  |  |  | Undertake 1No. medical screening for 1000No. food vendors and obtain valid medical certificate | All Town/Area Councils | X | X | X | X | 1400 |  | 35000 | [5 empty] | EHU | DA
71 |  |  |  |  | Education for Food Handlers | Assembly Conference Hall | X | X | X | X | 1000 |  | 19000 | [5 empty] | EHU | DA
72 |  |  |  |  | Organize 1 No workshop and sensitization for Skilled Artizans | Assembly Conference Hall | X | X | X | X | 1752 |  | 35456.24 | [5 empty] | EHU | DA
73 |  |  |  | Total | [6 empty] | 20024.2 |  | 543346.24
74 |  | Eradicate poverty in all its forms and dimensions |  | Social Welfare and Community Development | Register 100 LEAP beneficiaries and Indigents under the Free NHIS | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
75 |  |  |  |  | Undertake five LEAP Cycle Payment | District wide | x | x | x | x |  |  |  |  | 94482 |  |  |  | SWCD | DA
76 |  |  |  |  | Undertake five sensitization and monitoring of LEAP beneficiaries in twenty nine LEAP communities | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
77 |  |  |  |  | Register and update 50 PWDs, the aged and orphance database for support services | District wide | x | x | x | x |  |  | 2000 | [5 empty] | SWCD | DA
78 |  | Reduce income disparities among socio-economic groups and between geographical areas |  |  | Undertake four PWD Funds Disbursement to 100 beneficiaries. (Purchase Economic Items) | District wide | x | x | x | x |  |  | 100000 | [5 empty] | SWCD | DA
79 |  |  |  |  | Grant to PWDs (Medical and Financial Support) | District wide | x | x | x | x |  |  | 29425 | [5 empty] | SWCD | DA
80 |  | Ensure effective child protection and family welfare system |  |  | Train 50 registered PWDs (capacity building) | District wide | x | x | x | x |  |  | 10000 | [5 empty] | SWCD | DA
81 |  |  |  |  | Undertake Four PWDs meeting and monitoring | District wide | x | x | x | x |  |  | 10575 | [5 empty] | SWCD | DA
82 |  |  |  |  | Orientation of food vendors and school feeding programme contractors on nutrition | District wide | x | x | x | x |  |  | 15000 | [5 empty] | SWCD | DA
83 |  | Ensure the rights and entitlements of children |  |  | Undertake Monitoring and Registration of Ten Day-Care Centres. | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
84 |  | Enhance the wellbeing of the aged |  |  | Undertake Ten (10) Child Rights Protection and Promotion Sensitisation | Disterict wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
85 |  | Promote economic empowerment of women |  |  | Undertake Ten (10) community Mobilisation on socio-economic, health, disabled and girls and women in decision making. | District office | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
86 |  | Strengthen social protection, especially for children, women, persons with disability and the elderly |  |  | Undertake community entry and sensitization under the UNICEF Child Protection | District office | x | x | x | x |  |  | 3000 | [5 empty] | SWCD | DA
87 |  | Promote participation of PWDs in politics, electoral democracy and governance |  |  | Undertake five one (1) Gender sensitisation (women empowerment, voting for women assembly members, gender-base violence for PWD women and girls.) | Districtwide | x | x | x | x |  |  | 1000 | [5 empty] | SWCD | DA
88 |  | Ensure that PWDs enjoy all the benefits of Ghanaian citizenship |  |  | Case Management (Follow-up and Monitoring (UNICEF Child Protection) | Districtwide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
89 |  |  |  |  | Conduct, write and sunmit five (5) social enquiry reports on family Tribunal, Juvenile Court cases and maintenance cases. | District wide | x | x | x | x | 1000 | [7 empty] | SWCD | DA
90 |  |  |  |  | Gender Mainstreaming into infrastructures Development (WASH) | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
91 |  |  |  |  | Fellow up on Gender Mainstreaming into Natural Leaders under WASH Programme | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
92 |  |  |  |  | Registration and Monitoring of Day-Care Centres in the District | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
93 |  |  |  |  | Undertake 4 DEOC Meetings | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
94 |  |  |  |  | Monitor one Temporary Shelter in the District | District wide | x | x | x | x |  | 1000 | [6 empty] | SWCD | DA
95 |  |  |  |  | Monitor Gender and Child Protection Communities in Twenty (20) communities to cater for child labour, forced labour, child trafficking. | Districtwide | x | x | x | x |  | 2000 | [6 empty] | SWCD | DA
96 |  | Promote effective participation of the youth in socioeconomic development |  | Total | [6 empty] | 1000 | 13000 | 171000
97 |  |  |  | Total | [6 empty] | #REF! | #REF! | #REF! |  | #REF!
98 |  | Promote proactive planning for disaster prevention and mitigation |  | Disaster Prevention and Management | Organize 1No. fire education | All Towns/Area Councils | x |  | x |  | 0 | 2000 | 4000 | 0 | 0 |  |  |  | NADMO | DA
99 |  | Address recurrent devastating floods |  |  | Organise 4No. flood,raindstorm and pandemics education | All Towns/Area Councils |  | x |  |  | 0 | 1800 | 4600 | 0 | 0 |  |  |  | NADMO | DA
100 |  |  |  |  | Organise 1No. sensitization and awareness creation on disasters | All Towns/Area Councils | x |  | x | x | 0 | 2200 | 4900 | 0 | 0 |  |  |  | NADMO | DA
101 |  |  |  |  | Create 1No. Disaster Volunteer Group Creation (DVG) in each zones | All Towns/Area Councils |  | x |  |  | 0 | 2100 | 4100 | 0 | 0 |  |  |  | NADMO | DA
102 |  |  |  |  | Support disaster affected individuals | All Towns/Area Councils | x | x | x | x |  |  |  | 5000 |  |  |  |  | NADMO | DA
103 |  |  |  |  | Support Tree planting exercise in District | All Towns/Area Councils |  | x |  |  |  |  | 7000 | [5 empty] | NADMO | DA
104 |  |  |  |  | Organise 1No. World Disaster Reduction Day (WDRD) | All Towns/Area Councils |  |  |  | x | 0 | 1900 | 4400 | 0 | 0 |  |  |  | NADMO | DA
105 |  | Promote proper maintenance culture |  | Total | [7 empty] | 10000 | 29000
106 |  | Improve efficiency and effectiveness of road transport infrastructure and services | Infrastructure Delivery and Management | Infrastructure Development | Undertake 1No. Inventory on public buildings within the district | District wide |  |  | x |  | 0 | 6000 | 0 | 0 | 0 | 0 |  |  | Works Department | DA
107 |  |  |  |  | Undertake 1No. Inventory and assessment of Bridges and Culverts within the district | District wide | x |  |  |  | 7000 | 5300 | 0 | 0 | 0 | 0 |  |  | Works Department | DA
108 |  |  |  |  | Undertake 1No. Training of Staff in Contract Administration & Management | Breman Asikuma |  | x |  |  | 3000 |  | 0 | 0 | 0 | 0 |  |  | Works Department | DA
109 |  |  |  |  | Development Control | District wide | x | x | x | x | 7000 | 3000 | 0 | 0 | 0 | 0 |  |  | Works Department | DA
110 |  |  |  |  | Reshapping of 20km roads | All Towns/Area Councils | x | x | x | x | 920000 | 0 | 0 | 0 | 0 | 0 |  |  | Works Department | DA
111 |  |  |  |  | Replacement of Street lights | Domeabra | x | [5 empty] | 10000 | [5 empty] | DWD/ECG | DA
112 |  |  |  |  | Procurement of 1no. Grader | Asikuma |  | x |  |  |  | 360000 | [6 empty] | DWD | DA
113 |  |  |  |  | Accident Spot Data Collection | Asikuma |  | x |  |  |  | 1000 | [6 empty] | DWD/GPS | DA
114 |  |  |  |  | Fixing of streetlights | Bedum |  | x |  |  |  |  | 10000 | [5 empty] | DWD/ECG | DA
115 |  |  |  |  | Completion of 3 unit lockable stores | Asikuma |  |  | x |  | 89952 | [7 empty] | DWD | DA
116 |  |  |  |  | Completion of Retaining wall and filling of approaches at Teachers Abeka bridge | Asikuma |  | x |  |  |  |  | 473062.7 | [5 empty] | DWD | DA
117 |  |  |  |  | Completion of 7 unit Stores | Asikuma |  |  | x |  | 198417 | [7 empty] | DWD | DA
118 |  |  |  |  | Construction of Health Centre with 10 bed capacity at Bedum | Bedum |  |  |  | x |  |  | 917792 | [5 empty] | DWD | DA
119 |  |  |  |  | Completion of 1no. 1.2m 3-cellconcrete pipe culvert and 100m length 0.9 concrete u-drain | Brakwa |  | x |  |  |  |  | 406695.9 | [5 empty] | DWD | DA
120 |  |  |  |  | Road Safety Sensitization | Asikuma-Odoben-Brakwa |  |  | x |  |  | 6000 | [6 empty] | DWD/GPRTU | DA
121 |  |  |  |  | Supervision of Development Projects | District wide | x | x | x | x | 4100 | 0 | 0 | 0 | 0 | 0 |  |  | Works Department | DA
122 |  |  |  |  | Completion of Community Centres | Kokooso, Ato Dawuda |  |  | X |  |  |  | 80000 | [5 empty] | DWD | DA
123 |  |  |  |  | Renovation of Ambulance Bay | Asikuma |  | x |  |  |  |  | 45650 | [5 empty] | DWD | DA
124 |  |  |  |  | Renovation of main Assembly Block | Asikuma |  |  | x |  |  |  | 484726 | [5 empty] | DWD | DA
125 |  |  |  |  | Extension of Power from Edumamum town to Edumamum CHPS | Edumanamum | x | x | x | x |  | 60625.1 |  | 0 | 0 | 0 |  |  | Works Department | DA
126 |  |  |  | Total | [6 empty] | 1229469 | 441925.1
127 |  | Promote sustainable, spatially integrated, balanced and orderly development of human settlements |  | Spatial planning | Prepare 2No. local plans | Mwomaso | x | x | x | x | 20254.6813 | 2020 | 8400 | 0 | 0 | 0 |  |  | Physical Planning | DA
128 |  |  |  |  | Complete street naming and property addressing | Odoben | x | x | x | x | 19254.6813 | 2420 | 8000 | 0 | 0 | 0 |  |  | Physical Planning | DA
129 |  |  |  |  | Prepare 1No. district map | All Town/Area Councils | x | x | x | x | 25254.6813 | 2220 | 8400 | 0 | 0 | 0 |  |  | Physical Planning | DA
130 |  |  |  |  | Prepare 1No. spatial Plans (SDF, Structure plan) | All Town/Area Councils | x | x | x | x | 22254.6813 | 3320 | 8400 | 0 | 0 | 0 |  |  | Physical Planning | DA
131 |  |  |  |  | Undertake 1No. Sensitisation of communities on permitting and development control | All Town/Area Councils | x | x | x | x | 24254.6813 | 2120 | 8400 | 0 | 0 | 0 |  |  | Physical Planning | DA
132 |  |  |  | Total | [6 empty] | 111273.4063 | 12100 | 41600
133 | Maintain A Stable, United and Safe Society | Enhance quality of life in rural areas | Management and Administration | Legislative Oversight | Undertake 2No. Popular Participation in decision making/Town Hall meetings | All Town/Area Councils | X | X | X | X | 12000 | 60000 | 78342 | 12000 | 0 | 0 |  |  | ADMIN | DA
134 |  |  |  |  | Support Anti- Corruption Activities [NACAP] | District-wide | X | X | X | X | 10000 | 20000 | 34923 | 10000 | 0 | 0 |  |  | ADMIN | DA
135 |  |  |  |  | Procure Logistics & Supports to Sub-Structures | All Town/Area Councils | X | X | X | X | 15000 | 40000 | 22549 | 15000 | 0 | 0 |  |  | ADMIN | DA
136 |  |  |  |  | Pay Utility and other charges | Central Administration | X | X | X | X | 30000 | 30000 | 39213 | 30000 | 0 | 0 |  |  | ADMIN | DA
137 |  |  |  |  | Pay NALAG Dues | Central Administration | X | X | X | X | 9000 | 66000 | 31987 | 9000 | 0 | 0 |  |  | ADMIN | DA
138 |  |  |  |  | National Celebration | Central Administration | X |  |  | X |  |  | 10000 | [5 empty] | ADMIN | DA
139 |  | Deepen political and administrative decentralisation |  |  | Support Administrative & Technical Meetings | Central Administration | X | X | X | X | 20000 | 45912 | 34908 | 20000 | 0 | 0 |  |  | ADMIN | DA
140 |  |  |  |  | Servicing General Assembly and other sub-committee meetings | Central Administration | X | X | X | X | 40000 | 40000 | 55821 | 40000 | 0 | 0 |  |  | ADMIN | DA
141 |  |  |  |  | Organize 1No. End of Year Parcels & Best Worker Award | Central Administration | X | X | X | X | 30000 | 70000 | 37664 | 30000 | 0 | 0 |  |  | ADMIN | DA
142 |  |  |  |  | Support Staff Welfare | Central Administration | X | X | X | X | 10000 | 45000 | 24998 | 10000 | 0 | 0 |  |  | ADMIN | DA
143 |  |  |  |  | Support to Cultural Activities | Central Administration | X | X | X | X | 7000 | 59000 | 25897 | 29879 | 0 | 0 |  |  | ADMIN | DA
144 |  |  |  |  | Pay all due Compensation | Central Administration | X | X | X | X | 2000 | 43000 | 34562 | 39213 | 0 | 0 |  |  | ADMIN | DA
145 |  |  |  |  | Support Security Management (DISEC & Other Related Activities) | Central Administration | X | X | X | X | 3000 | 19000 | 39554 | 27453 | 0 | 0 |  |  | ADMIN | DA
146 |  |  |  |  | MP's Constituency Support [ Programmes] | Central Administration | X | X | X | X | 1900 | 90000 | 32568 | 1900 | 0 | 0 |  |  | ADMIN | DA
147 |  |  |  |  | Support Official and National Celebrations | Central Administration | X | X | X | X | 10000 | 24983 | 29564 | 10000 | 0 | 0 |  |  | ADMIN | DA
148 |  | Promote the fight against corruption and economic crimes |  |  | Preparation and Review of Strategic documents: MTDP 2022 FFR and Composite Budget, DESSAP, etc | All Town/Area Councils | X | X | X | X | 15000 | 15000 | 43213 | 15000 | 0 | 0 |  |  | ADMIN | DA
149 |  |  |  |  | Construction of 3No. Security Post | Nwomaso, Odoben and Swedru Road | x | x | x | x |  | 15000 |  |  | 0 | 0 |  |  | ADMIN | DA
150 |  | Enhance public safety |  |  | Surfacesealing | Odoben SHS | x | x | x | x |  | 10000 |  |  | 0 |  |  |  | ADMIN | DA
151 |  |  |  |  | Undertake 4No. publicity activities | All Towns/Area Councils | x | x | x | x |  | 1500 | [6 empty] | INFOR. | DA
152 |  |  |  |  | Organise and arrange 4No. public address systems | All Towns/Area Councils | x | x | x | x |  | 600 | [6 empty] | INFOR. | DA
153 |  |  |  |  | Setting up of 1No. NHIS sub-office | Odoben | x | x | x | x | 0 | 0 | 0 | 0 |  |  |  |  | NHIS | DA
154 |  |  |  | Total | [6 empty] | 214900 | 694995 | 575763 | 299445
155 |  | Improve decentralised planning |  | Human Resource | Train Newly Assembly Members on models standing orders | AOB District Assembly Hall |  | √ |  |  | 7000 | 0 | 0 | [5 empty] | HR | DA
156 |  |  |  |  | Organize training on environmental management and pest control | AOB District Assembly Hall |  |  | √ |  | 7366 | 0 | 0 | [5 empty] | HR | DA
157 |  |  |  |  | Organize workshop for staff on LGS on performance management systems on apperials | AOB District Assembly Hall |  |  |  | √ | 12000 | 0 | 0 | [5 empty] | HR | DA
158 |  |  |  |  | Organize 1No Sensitization of staff on LGS Protocols | AOB District Assembly Hall | √ |  |  |  | 2530 | 0 | [6 empty] | HR | DA
159 |  |  |  | Total | [6 empty] | 28896 | 0 |  | 0
160 |  | Strengthen fiscal decentralisation |  | Finance and Revenue Mobilization | Conduct 4No. Revenue Mobilization and other treasury Activities | All Town and Area Council | x |  | x |  | 2000 | [7 empty] | Finance | DA
161 |  |  |  |  | Update Accounting Software | All Town and Area Council |  | x |  |  | 2000 | [7 empty] | Finance | DA
162 |  |  |  |  | Organize 4No. meeting for revenue collectors | All Town and Area Council | x |  | x | x | 3000 | [7 empty] | Finance | DA
163 |  |  |  |  | Organise4No. Sensitization of Communities on Tax Education and Government Policies and Programmes | All Town and Area Council |  |  |  | x | 2100 | [7 empty] | Finance | DA
164 |  |  |  |  | 4No.Public Education on Revenue mobilization | All Town and Area Council | x | x | x | x | 3000 | [7 empty] | Finance | DA
165 |  |  |  | Total | [6 empty] | 12100
166 |  | Deepen transparency and public accountability |  | Planning, Budgeting, Monitoring and Evaluation | Undertake 4No. Valuation & Re-valuation of Properties | Central Administration | X | X | X | X | 2000 | 61459 | 39459 | 35218 |  |  |  |  | ADMIN | DA
167 |  |  |  |  | Update Revenue and Socio -Economic Data [TREE] | Central Administration | X | X | X | X | 1000 | 19672 | 28911 | 44234 |  |  |  |  | ADMIN | DA
168 |  |  |  |  | Procure Building Materials to support Self Help Project/Counterpart Funding | District-wide | X | X | X | X | 30000 | 30000 | 39899 | 30000 |  |  |  |  | ADMIN | DA
169 |  | Enhance capacity for policy formulation and coordination |  |  | Procure other office consumables | Central Administration | X | X | X | X | 9000 | 48231 | 30000 | 29598 |  |  |  |  | ADMIN | DA
170 |  |  |  |  | Conduct 1No. Projects Management exercises | District-wide | X | X | X | X | 2000 | 18000 | 37934 | 38453 |  |  |  |  | ADMIN | DA
171 |  |  |  |  | Procure Office Logistics | Central Administration | X | X | X | X | 10000 | 54000 | 49823 | 10000 |  |  |  |  | ADMIN | DA
172 |  |  |  |  | Host all Official Guest | Central Administration | X | X | X | X | 8000 | 35879 | 38945 | 44231 |  |  |  |  | ADMIN | DA
173 |  |  |  |  | Service and Maintain official vehicles | Central Administration | X | X | X | X | 10000 | 93000 | 24000 | 37897 |  |  |  |  | ADMIN | DA
174 |  |  |  |  | Pay for Running Cost of official Vehicles | Central Administration | X | X | X | X | 25000 | 65000 | 37000 | 27435 |  |  |  |  | ADMIN | DA
175 |  |  |  |  | Undertake 1No. Maintenance of Equipment | Central Administration | X | X | X | X | 30000 | 30000 | 34000 | 42456 |  |  |  |  | ADMIN | DA
176 |  |  |  |  | Renew official Vehicle Insurance | Central Administration | X | X | X | X | 10000 | 89000 | 10453 | 10342 |  |  |  |  | ADMIN | DA
177 |  |  |  |  | Undertake 1No. Supervision & Regulation of Infrastructure Developments | DPCU Secretariat | X | X | X | X | 12000 | 30000 | 3876 | 33000 |  |  |  |  | ADMIN | DA
178 |  |  |  |  | Undertake 1No. Internal Management of organization | Central Administration | X | X | X | X | 1894 | 47000 | 12345 | 17000 |  |  |  |  | ADMIN | DA
179 |  |  |  |  | Renovation & Repairs Works on 5No. Staff Residential Accommodation | Central Administration | X | X | X | X | 9783.4 | 17870.74 | 9453 | 45686.84 |  |  |  |  | ADMIN | DA
180 |  |  |  |  | Procure Disinfectants, Insecticides, and Repellants [Local Fumigation] | District wide | X | X | X | X | 3000 | 86200 | 3231 | 32891.56 |  |  |  |  | ADMIN | DA
|  |  |  | Total | [6 empty] | 163677.4 | 725311.74 | 399329 | 478442.4